## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Understand negotiation system and define workflow | MUST HAVE | No Dependency | Kavya Sri | Completed
S1 | S1 | US-002 | Implement Scenario Selection for 3 predefined scenarios | MUST HAVE | No Dependency | Kavya Sri | Completed
S1 | S1 | US-003 | Define agent personas with roles, goals and constraints | MUST HAVE | Scenario Selection | Team | Completed
S1 | S1 | US-004 | Build Agent Configuration UI | MUST HAVE | Scenario Data | Kavya Sri | Completed
S1 | S1 | US-005 | Add personality selection for agents | MUST HAVE | Agent Configuration | Kavya Sri | Completed
S1 | S1 | US-006 | Display agent goals and constraints | MUST HAVE | Agent Configuration | Kavya Sri | Completed
S1 | S1 | US-007 | Prepare System Architecture | MUST HAVE | Workflow Design | Kavya Sri | Completed
S1 | S1 | US-008 | Add README and MIT License to GitHub repository | MUST HAVE | GitHub Repository | Team | Completed
S2 | S2 | US-009 | Develop Orchestrator Agent | MUST HAVE | Agent Configuration | Team | In Progress
S2 | S2 | US-010 | Implement LLM-powered Agent Reasoning Engine | MUST HAVE | Orchestrator | Team | Not Started
S2 | S2 | US-011 | Implement Counteroffer Evaluation and Concession Module | MUST HAVE | Agent Reasoning | Team | Not Started

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T-001 | Understand negotiation and define workflow | [5 empty] | 2
US-002 | T-002 | Implement Scenario Selection for 3 predefined scenarios | [5 empty] | 3
US-003 | T-003 | Define agent personas with roles,goals and constraints | [5 empty] | 2
US-004 | T-004 | Build Agent Configuration UI | [5 empty] | 4
US-005 | T-005 | Add personality selection for agents | [5 empty] | 2
US-006 | T-006 | Display agent goals and constraints |  |  |  |  | 3- Completed | 2
US-007 | T-007 | Prepare System Architecture | [5 empty] | 2
US-008 | T-008 | Add README and MIT License to GitHub repository | [5 empty] | 1

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 1 | None | Understood negotiation system and defined the basic workflow | Understood negotiation system and defined the basic workflow
S1 | Day 2 | None | Implemented scenario selection for the 3 predefined scenarios
S1 | Day 3 | None | Defined agent personas with roles,goals,contraints and personalities
S1 | Day 4 | None | built the Agent Configuration UI
S1 | Day 5 | None | Added personalit selection and displayed agent goals and contraints
S1 | Day 6 | None | prepared the system architecture and connected the basic workflow
S1 | Day 7 | None | Updated README,added MIT License and pushed completed work to GitHub

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2026-09-01 | 2026-09-07 | Kavya Sri | Planning tasks before implementation | Delaying documentation work | Regular GitHub updates and communication | Complete assigned UI and documentation tasks on time
2 | S1 | 2026-09-01 | 2026-09-07 | Chakri | Participate in development discussions |  | Team communication | Continue contributing to development tasks
3 | S1 | 2026-09-01 | 2026-09-07 | Mutheeswar | Participate in development discussions |  | Team coordination | Continue participating in assigned tasks
4
5
6
7